## screen_flow
Murraya Fashion Shop
B. Admin Journey (Back Office)
1. Admin Login | DONE | DONE
2. Dashboard | WORK_IN_PROGRESS | WORK_IN_PROGRESS
Overview of sales, orders, customers | WORK_IN_PROGRESS | WORK_IN_PROGRESS
3. Category Management | DONE | DONE
Add, edit, delete category | DONE | DONE
4. Product Management | DONE | DONE
Add, edit, delete products | DONE | DONE
5. Order Management | PENDING | PENDING
View & update order status | PENDING | PENDING
6. User Management | DONE | DONE
Manage customers & reviews | DONE | DONE

## 1. Admin Login
Murraya Fashion Shop
1. Admin Login | Api | UI | SERVICES
Main route | /admin/adminLoginForm | DONE | DONE
Forget password | /admin/adminForgetPasswordForm | DONE | DONE
Reset password | /admin/adminResetPasswordForm | DONE | DONE

## 2. Dashboard
Murraya Fashion Shop
Dashboard | Api | UI | SERVICES
Main route | /admin/adminDashboard | DONE | DONE
Total orders | /admin/adminDashboard | PENDING | PENDING
Total customers | /admin/adminDashboard | DONE | DONE
Total sales | /admin/adminDashboard | PENDING | PENDING

## 3. Category Management
Murraya Fashion Shop
Category Management | Api | UI | SERVICES
Main route | /admin/categoryManagement | DONE | DONE
List all categories | /admin/categories | DONE | DONE
Add Category | /admin/addCategory | DONE | DONE
Edit Category | /admin/updateCategories/{categoryId} | DONE | DONE
Delete Category | /admin/deleteCategories/{categoryId} | DONE | DONE

## 4. Product Management
Murraya Fashion Shop
Category Management | Product Management | UI | SERVICES
Main route | /admin/productManagement | DONE | DONE
List all products | /admin/productManagement | DONE | DONE
Add Product | /admin/addProduct | DONE | DONE
Edit Product | /admin/updateProduct/{productId} | DONE | DONE
Delete Product | /admin/deleteProduct/{productId} | DONE | DONE
Delete Product image | /admin/deleteProductImage/{imageId} | DONE | DONE
View Product info | /admin/viewProduct/{productId} | DONE | DONE
Product Details route | /admin/viewProductDetails/{productId} | DONE | DONE
Upload Product image | /admin/uploadProductImages/{productId} | DONE | DONE
View Product image by ImageId | /admin/productImage/{imageId} | DONE | DONE
View all Product images | /admin/productImages/{productId} | DONE | DONE

## 5. Order Management
Murraya Fashion Shop
Order Management | Api | UI | SERVICES
Main route
View order status
Update order status

## 6. User Management
Murraya Fashion Shop
| User Management | Api | UI | SERVICES
| Main route | /admin/userManagement | DONE | DONE
ACTIVATE | Manage customers | /userManagement/updateUserStatus/${row.userId}/2 | DONE | DONE
DEACTIVATE |  | /userManagement/updateUserStatus/${row.userId}/1 | DONE | DONE
| Review Management | /admin//productReviewsManagement | DONE | DONE
| Reviews | /admin/reviews/ + productId | DONE | DONE
|  | /admin/products | DONE | DONE

## 7. Product Reviews
Murraya Fashion Shop
Review Management | Api | UI | SERVICES
Main route | /admin//productReviewsManagement | DONE | DONE
Reviews | /admin/reviews/ + productId | DONE | DONE
| /admin/products | DONE | DONE

## 8.Product Discounts
Murraya Fashion Shop
Product Discount Management | Api | UI | SERVICES
Main route | /admin/discountManagement | DONE | DONE
Discounts apply/remove to product | /admin/discounts/apply | DONE | DONE
| /admin/discounts/applyDiscount | DONE | DONE
| /admin/discounts/removeDiscount | DONE | DONE
Create discount | /admin/discounts/addDiscount | DONE | DONE
Update discount | /admin/discounts/updateDiscount/{discountId} | DONE | DONE
Delete discount | /admin/discounts/deleteDiscount/{discountId} | DONE | DONE
View discount | /admin/discounts//viewDiscount/{discountId} | DONE | DONE

## status
PENDING
WORK_IN_PROGRESS
DONE
Murraya Fashion Shop
| Status | Api | UI | SERVICES
| View all status | /admin/status/allStatuses | PENDING | DONE